## Slide 1: MOSH Falls of Ground Team Leading Practice Adoption Team Activity Report 20 June 2014
Chris Legodi, Andre van Zyl and Duncan Adams

## Slide 2
Contents
Mission and Values reminder
Plan for 2014
Progress May / June 2014

## Slide 3
Leading the change to zero harm
Mission and Values - MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values

## Slide 4
EE&MS
EE&MS & TARP (FOG)
Facilitation in the Coal Industry
FOG Adoption Team Planner 2014
Prevention of All Uncontrolled Falls of Ground
Jan 14 | Feb 14 | Mar 14 | Apr 14 | May 14 | Jun 14 | Jul 14 | Aug 14 | Sep 14 | Oct 14 | Nov 14 | Dec 14
EE&MS
Integration with TARP for FOG
Bolts with Nets
TARP
Integrate with EE&MS – Harmony, Sibanye Gold, Two Rivers, Wessels, Nkomati, Modikwa, Dwarsrivier....
Workplace Illumination
No Leading Practice Found – put on back burner
Leading Practice for Optimised Drilling and Blasting
Consult widely with Role-players
Call for “Day of Learning” 5 Nov 14
Initiate Process to start the Leading Practice Adoption Process
Plan
Continue with Facilitation within the Coal Industry
Glenburn Lodge Consultative Programme ?

## Slide 5
No` | Activities
1 | Tripartite forums visited and positively participated . (NC, Free State, Merafong, Vaal River, Limpopo)
2 | Pilot Team established and initiating the integration process for EE&MS & TARP (FoG)
3 | Special assistance to: Harmony Mines (Coordinating TARP Adoption ), Sibanye Gold (Pilot -integration of TARP en EE&MS also for upgrading of TARP (FoG) Hernic (Assisting with Training for Interviews Mental Models etc.) Mintails (New start for “small mines”) – EE&MS and TARP (FoG) Bakubung (Change from Vertical Sinking to Station Cutting – EE&MS and Tarp) Venetia Mine (EE&MS Review and TARP) SAMANCOR Chrome – Eastern Chrome Mines (Review EE&MS and start with TARP) Kimberley Diamond Mines (EE&MS and TARP) Koffiefontein Diamond Mine (EE&MS and TARP)
4 | Three COPAs run in Central, Northern Cape and Mpumalanga / Limpopo Regions for FoG Leading practices
5 | Renewed interest from diamond mines. Petra diamonds and De Beers. Call for formation of a possible Diamond COPA (Finsch Diamond Mine – Leading Adoption Site)
Progress for the Month of May / June 2014
Leading the change to zero harm

## Slide 6
Progress for the Month of April/May/June 2014
No | Challenge (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
1 | Quality Nets and bolts installations in low stoping widths (<120cm) | Directed and Focused COPA with Supplier Displays at Randfontein GC – Machines, Nets, Bolts etc. | 11 April 20 Successfully Completed | Team
2 | Helping mines to develop Mental Models, LBP’s, BCP’s, and complete Portfolios of Evidence before reporting | Discussions at COPAs, and on special requests from individual mines | May 2014 On Going….. Herhaaal, Herhaal, Herhaal….. | Team
3 | Too many practices for mines to cope with | Pilot Initiatives with Sibanye Gold and Phakisa | May 2014 | DJA & RM
4 | Lack of human resources on mines to effectively carry out adoption | Trial at Phakisa – Use line personnel | June 2014 | DJA
5 | Mines in General do not appreciate the importance of LB and BC plans | Marketing Drive required, starting with MOSH TASK FORCE, MPA’s, TPF’s COPA’s – all occasions….. | June 2014 On going….. | AvZ DJA CL
Leading the change to zero harm

## Slide 7
Leading Practice Adoption
Leading the change to zero harm
Leading Practice | Progress Tracker | No. of Mines Participating
Entry Examination and Making Safe | 98% | 69
Nets with Bolts (Stoping Areas) | 94% | 44
Triggered Action Response Plan (FoG) | 64% | 47

## Slide 9
CENTRAL COPA – Netting with Bolting and TARP