## Slide 1: MOSH Falls of Ground Team Leading Practice Adoption Team Activity Report
22 January 2015

## Slide 2
Contents
Mission and Values reminder
Plan for 2015 and beyond
Progress August / September 2014

## Slide 3
Leading the change to zero harm
Mission and Values - MOSH
To facilitate the adoption of leading practice through a people oriented process to significantly improve occupational health and safety in the minerals industry
Our ultimate goal is the provision of working conditions that are free from harmful effects
Values

## Slide 4
No` | Activities
1 | Central COPA for Netting with Bolting, TARP and integration of TARP and Entry Examination &Making Safe.
2 | Northern Cape COPA
3 | Eastern Limb COPA
4 | Involvement with Tripartite Fora (Free State, NW, Limpopo, Klerksdorp and Merafong)
5 | Investigation and report on Ledging in the industry (Report back to CEOs - First Quarter)
7 | Position paper on drilling and blasting. Consideration of Drilling and Blasting as a new Leading Practice.
Planning for 2015
Leading the change to zero harm

## Slide 5
Facilitation in the Coal Industry
FOG Adoption Team Planner 2015
Prevention of All Uncontrolled Falls of Ground
Jan 15 | Feb 15 | Mar 15 | Apr 15 | May 15 | Jun 15 | Jul 15 | Aug 15 | Sep 15 | Oct 15 | Nov 15 | Dec 15
TARP COPAs
Bolts with Nets COPA
Integration of TARP into EE&MS
Ledging Investigation
Drilling and Blasting investigation
Planning
Possible Ledging Leading Practice
Possible drilling and blasting leading practice

## Slide 6
Challenges to be addressed in 2015
No | Challenge (Issues, Risks, Concerns) | Response - Remedial Action | Due Date | Resp. Person
1 | Lack of Senior Management present at COPA meeting and involved in the mine process | Ask GMs to give presentations of MOSH LP progress at their mines. Ask the mine to “host” the COPA meeting. Peer reviews. | April 2015 | Team
2 | Support, uniformity and continuity at and between all regional COPA meetings | All members of the FoG team will attempt to be present at all FoG COPA meetings | On-going | Team
3 | Support of other team COPAs to learn and help | Representation of FoG team at other COPA meetings | On-going | Team
4 | Recognition and reward for mines completing an adequate PoE | Review document for evaluating a PoE. Presentation of certificate by Head of the Learning Hub at regional Tripartite Forum Meetings (See Strategic plan, Goal 2, Action plan vi) | March 2015 | Teams and SM
Leading the change to zero harm

## Slide 7
Leading Practice Adoption
Leading the change to zero harm
Leading Practice | Progress Tracker | Approximate No. of People Affected
Entry Examination and Making Safe | 98% | 69000
Nets with Bolts (Stoping Areas) | 97% | 30000
Triggered Action Response Plan (FoG) | 69% | 27000