## Slide 1: Noise Adoption Team
19th March 2015

## Slide 2
 | Contents
 | Key activities/highlights of the month Past & Future activities Lowlights Questions

## Slide 3
Key Team activities for the Months (Feb’ 15 – Mar ‘15)
 | Highlights (Achievements, Industry Interactions)
1. | HPD_TAS Adoption Impala Platinum Self requested verification (Mid April 2015) Marula Platinum - Follow up meeting Establishing Mine Adoption Team PPC Mooiplaas Interviewer training 20 March 15. (Late comer) On par with action plan BHP Becsa Middelburg Colliery 06th March 2nd meeting Induction training done (Late comer) Establishing Mine Adoption Team & roll out plan Exxaro Meeting 19th Feb 2015 Mosh Task Force members intervention. Groote Geluk invite 9th April 2015. (Late comer) Matla 1 Pilot shaft – Followed up March 2015

## Slide 4
Key Team activities for the Months (Feb’ 15 – Mar ‘15)
 | Highlights (Achievements, Industry Interactions)
1. | HPD_TAS Adoption (Cont) Glencore Coal Impunzi Mine 26th March 2015 VOHE introduction meeting. (Late comer) Sasol Restructuring slowing progress . Intervention meeting 27th March 2015. 3 Day internal workshop set Aquarius Platinum – Induction training postponed. (Late comer) ARM TRP – HPD Case study input from LH. 25th February 2015. (Finalising report and brochure) Black Rock Operations. Restructuring slowing progress. 26th March 2015. AGA POE progress verification. 12th March 2015. (PoE 65% completed). Copa Meeting 12 March 2015 7 Mining Houses attended (PPC, Exxaro, AGA, ARM, Sasol, Anglo Platinum, Impala Platinum)

## Slide 5
Key Team activities for the Months (Feb’ 15 – Mar ‘15)
 | Highlights (Achievements, Industry Interactions)
2. 3. | IBMQI 05th March 2015 – Project charters for different sub-working groups. Feedback session to GEE’s on 13th March 2015 Feedback session with CM&EE’s - 26th March 2015 Roadshows – AMMSA, Tri-partite meetings Hearing Conservation Noise Presentation LHAC, North West Tri-partite, HPD Copa members Free State Tri-partite 2nd April 2015.

## Slide 6
Key Team activities for the Months (Feb’ 15 – Mar ‘15)
No | Activities
4. | Several meetings were held during 19 Feb 2015 & 19 Mar 2015 Limpopo Noise Task team meeting 24 Feb 2015 next meeting 31st March 2015 North West Regional tri-partite meeting team meeting 05th March 2015 Free State Tri-partite meeting. 05th March 2015 IBMQI Meeting. 05th March 2015, next meeting 25th March 2015 at Lonmin GEE meeting. 13th March 2015 Mpumalanga Tri-partite meeting 24th March 2015. Quarries & Surface mines 25th March Eastern limb Tri-partite meeting at Modikwa Mpumalanga Tri-partite meeting 18th Feb 2015. Reviewing Noise Expert Model
Past & future activities

## Slide 7
No | Activities | Lowlights (Issues, Risks, Concerns) | Response - Remedial Action
1. | HPD Adoption | Slow progress after several interventions | Escalate to Mosh Task Force
2. |  |  | 
3. |  |  | 
4. |  |  | 
5. |  |  | 
6. |  |  | 
Lowlights – For the Month (Feb’ 15 – Mar ‘15)

## Slide 8
 | (Feb’ 15 – Mar ‘15)
 | Thank You.